## Risks
high/medium/low
Risk | Discription | Raised By | Impact | Probability
Infrastructure setup and maintenance | Not being in the optimal position to setup and maintain the infrastructure, due to upskilling and resource constriants | Elton | High | High
Credit card number in the clear | Credit card number in the existing system (Netplus) is sent to the front end in the clear. Possibility of bringing the project into PCI Scope | Elton | High | Low
Payments | Current Batch process of upfront validation does not match OOTB process | Elton | High | Low
Entitlements | BB entitlements are very different to current platform rules, the current rules are complex. This could lead to a difficult and lengthy Ingestion process | Mauro
Solution architect not dedicated to DXP | Applicable for all core team resources, they need to be dedicated to the the digital project | Elton | High | Medium
Regulatory / Compliance | Single compliance team member (Fabio) joined the compliance session on Thursday 17th March. But there are open questions RE PCI and if there are any compliance requirements we need to meet | Elton

## Actions
Actions | Responsible Person | Due Date
Setup infrastructure | Marcio
Complete TAD | Elton Plath | 2022-03-24
Email Fabio to confirm compliance requirements | Elton Plath | 2022-03-21
Finalise Service catalog - https://docs.google.com/spreadsheets/d/151l6ORd7dBVnOaNkdDoflF4Oygw34TzkEI0wP_iz4WM/edit#gid=0 | John Wati | 2022-03-22
Global and company Limits - is it possible to have different limits per channel (Web vs Mobile) | John Wati | 2022-03-22
Investigate adding custom validation for Batches upfront | Elton Plath | 2022-03-22
Create example Legal Entity structures, add to TAD | Elton Plath | 2022-03-22

## Questions
Question | Person | Answer
OS & Version (for Backbase components): JDK (for Backbase components): Oracle version: ActiveMQ version: IBM DataPower Gateway version: API Connect version: IBM ACE version: | Cris
Sonar - do you run sonarQube on-prem or are you using SonarCloud? |  | sonarQube
Container Registry - what will you be using for storing the docker images? |  | Nexus
Message broker, will you be using ActiveMQ or IBM ACE? How will commication work between ActiveMQ and ACE? | Cris | ActiveMQ, will need to bridge to IBM ACE Can we use IBM MQ rather than ActiveMQ?
Translation of error codes to description, how does it work? | Elton
Exchange Rate service, SBM to supply. current service is updated daily at 9am (or maybe 2x per day - is rate service used for limit check? - is rate service used for actual payment amount? | Cris / John
2 zone deployment, where are these zones located? | Cris
Transaction integration patterns - "inbound push" - Angola "outbound pull" - Kenya
Data retention policy, how long should we retain data for on BB platform? | Fabio
Data partitioning - customer expressed interest in data partitioning | Elton
Maintenance windows - ask Teodorico / Mauro? | Mauro
Ingestion / Migration, how? | Cris / Elton
Where is password stored, can we migrate the password? | Cris
Message translation on integration services - how is this done? | Elton
What are the requirements for non necessary cookies (user acceptance, etc.). User should accept or reject. Question: Will this be a popup, how will we do this? Cookies, is there a requirement to gain user consent before using analytics? | Mauro
200K current user base. Mauro to provide, but ~50k concurrent user sessions. We define sessions as user logged on | Mauro
Should be available 99.9% of the time. Mauro to discuss internally and revert | Mauro